## guidance
The PAS Neighbourhood Plan Project Management Tool |  |  |  | DROP DOWNS
hide before issuing
status
unknown
programmed
started
in progress
owner
local planning authority
neighbourhood
neighbourhood & LPA
How to use the Tool:
1. | Enter starting date for Plan Programme: |  | 2013-04-01
2. | Start by completing the task plan page (red tab):
| (a) | Add to/Edit the task list as required under each of the headings.
| (b) | Estimate the start and end time for each task. Indicative times are provided which allow
for the statutory minimum publicity periods.
| c) | You should enter information only into light green cells
You should not replace formulas within grey cells
You should not delete or insert cells, rows or columns. You can merge tasks (group two or more
and enter into a single row to ensure things fit). You can hide rows to make the
sheets more compact if required.
3. | The Gantt chart (project plan, yellow tab) will automatically update based on the task plan.
Prepared by:
NPPMT v1.1 07.01.14
The Neighbourhood Plan Project Management Tool is a way of planning how to produce and deliver a Neighbourhood Plan. It is a guide to the overall process and timescale for neighbourhood plan-making; giving the key headings of activities required and timings with an ability to add tasks to the tool to produce a timeline and production plan for a neighbourhood plan. The tool is for local planning authorities and parish councils or neighbourhood forums to use together to produce a neighbourhood plan.
This project management tool allows you to enter tasks and timings on the red 'task plan' tab. The 'task plan' lists the key task headings that will be required to produce a neighbourhood plan and gives indicative or required timescales for these task headings. The task headings that are the responsibility of the local authority have been highlighted in purple.
Entries on the 'task plan' tab are automatically transferred into a Gantt chart to produce a timeline for the production of the plan. The timeline can be found on the yellow 'Gantt' tab.
User notes:
a) The task list allows record the:
i) status of tasks (unknown, programme, started, in progress or blank)
ii) ownership of tasks (neighbourhood, neighbourhood & LPA, or add your own entry)
iii) start and finish time tasks
b) You can add extra task headings at the end of the task plan if required and they will be added to the bottom of the Gantt chart. For example, you could add additional tasks if a further round of consultation is appropriate following the emergence of new ideas from consultation or if a restructuring of the document arises.
c) The 'Referendum' task heading has a 28 day period statutory minimum for community lead plans and a 56 day statutory minimum for business lead plans noted. Use the period relevant to your plan.

## task plan
Task Plan
Task no. | Tasks / subtasks | status | owner | start | finish | Calendar Days
| Scoping aims for neighbourhood area/forum application |  |  | 2013-04-01 | 2013-05-01 | 30
1 | Indicative timescale |  | neighbourhood | 2013-04-01 | 2013-05-01 | 30
2
3
4
5
6
7
8
9
10
11
12
13
14
15
| Submission of neighbourhood area application |  |  | 2013-05-01 | 2013-05-15 | 14
16 | Indicative timescale |  | neighbourhood | 2013-05-01 | 2013-05-15 | 14
17
18
19
20
21
22
23
24
25
26
27
28
29
30
| Publicity for neighbourhood area application | 6 week minimum |  | 2013-05-16 | 2013-06-27 | 42
31 | Indicative timescale |  | local planning authority | 2013-05-16 | 2013-06-27 | 42
32
33
34
35
36
37
38
39
40
41
42
43
44
45
| Determination of neighbourhood area application |  |  | 2013-06-28 | 2013-08-09 | 42
46 | Indicative timescale |  | local planning authority | 2013-06-28 | 2013-08-09 | 42
47
48
49
50
51
52
53
54
55
56
57
58
59
60
| Publicity for the designation of a neighbourhood area |  |  | 2013-08-10 | 2013-08-17 | 7
61 | Indicative timescale |  | local planning authority | 2013-08-10 | 2013-08-17 | 7
62
63
64
65
66
67
68
69
70
71
72
73
74
75
| Submission of a neighbourhood forum application |  |  | 2013-05-01 | 2013-05-15 | 14
76 | Indicative timescale |  | neighbourhood | 2013-05-01 | 2013-05-15 | 14
77
78
79
80
81
82
83
84
85
86
87
88
89
90
| Publicity for the designation of a neighbourhood forum | 6 week minimum |  | 2013-05-16 | 2013-06-27 | 42
91 | Indicative timescale |  | local planning authority | 2013-05-16 | 2013-06-27 | 42
92
93
94
95
96
97
98
99
100
101
102
103
104
105
| Determination of a neighbourhood forum application |  |  | 2013-06-28 | 2013-08-09 | 42
106 | Indicative timescale |  | local planning authority | 2013-06-28 | 2013-08-09 | 42
107
108
109
110
111
112
113
114
115
116
117
118
119
120
| Publicity of the designation of a neighbourhood forum |  |  | 2013-08-10 | 2013-08-17 | 7
121 | Indicative timescale |  | local planning authority | 2013-08-10 | 2013-08-17 | 7
122
123
124
125
126
127
128
129
130
131
132
133
134
135
| Preparation of the Neighbourhood Development Plan: community engagement |  |  | 2013-04-01 | 2013-10-21 | 203
136 | Indicative timescale |  | neighbourhood | 2013-04-01 | 2013-10-21 | 203
137
138
139
140
141
142
143
144
145
146
147
148
149
150
| Preparation of the Neighbourhood Development Plan: evidence gathering |  |  | 2013-04-01 | 2013-10-21 | 203
151 | Indicative timescale |  | neighbourhood | 2013-04-01 | 2013-10-21 | 203
152
153
154
155
156
157
158
159
160
161
162
163
164
165
| Preparation of the Neighbourhood Development Plan: appraisals |  |  | 2013-06-28 | 2013-10-21 | 115
166 | Indicative timescale |  | neighbourhood | 2013-06-28 | 2013-10-21 | 115
167
168
169
170
171
172
173
174
175
176
177
178
179
180
| Preparation of the Neighbourhood Development Plan: drafting |  |  | 2013-06-28 | 2013-10-21 | 115
181 | Indicative timescale |  | neighbourhood | 2013-06-28 | 2013-10-21 | 115
182
183
184
185
186
187
188
189
190
191
192
193
194
195
| Pre-submission consultation and publicity of the proposed Neighbourhood Development Plan | 6 week minimum |  | 2013-10-22 | 2013-12-03 | 42
196 | Indicative timescale |  | neighbourhood | 2013-10-22 | 2013-12-03 | 42
197
198
199
200
201
202
203
204
205
206
207
208
209
210
| Revisions to draft Neighbourhood Development Plan |  |  | 2013-12-04 | 2014-01-03 | 30
211 | Indicative timescale |  | neighbourhood | 2013-12-04 | 2014-01-03 | 30
212
213
214
215
216
217
218
219
220
221
222
223
224
225
| Submission of draft Neighbourhood Development Plan to the Local Planning Authority |  |  | 2014-01-04 | 2014-01-05 | 1
226 | Indicative timescale |  | neighbourhood | 2014-01-04 | 2014-01-05 | 1
227
228
229
230
231
232
233
234
235
236
237
238
239
240
| Publication of Neighbourhood Development Plan | 6 week minimum |  | 2014-01-06 | 2014-02-17 | 42
241 | Indicative timescale |  | local planning authority | 2014-01-06 | 2014-02-17 | 42
242
243
244
245
246
247
248
249
250
251
252
253
254
255
| Appointment of Examiner |  |  | 2014-01-06 | 2014-02-10 | 35
256 | Indicative timescale |  | neighbourhood & LPA | 2014-01-06 | 2014-02-10 | 35
257
258
259
260
261
262
263
264
265
266
267
268
269
270
| Submit plan for examination |  |  | 2014-02-18 | 2014-02-19 | 1
271 | Indicative timescale |  | local planning authority | 2014-02-18 | 2014-02-19 | 1
272
273
274
275
276
277
278
279
280
281
282
283
284
285
| Examination |  |  | 2014-02-19 | 2014-04-02 | 42
286 | Indicative timescale |  | examiner | 2014-02-19 | 2014-04-02 | 42
287
288
289
290
291
292
293
294
295
296
297
298
299
300
| Council consideration of the Examiner's recommendations |  |  | 2014-04-03 | 2014-05-15 | 42
301 | Indicative timescale |  | local planning authority | 2014-04-03 | 2014-05-15 | 42
302
303
304
305
306
307
308
309
310
311
312
313
314
315
| Publication of Examiner's Report and Decision Statement |  |  | 2014-05-16 | 2014-05-17 | 1
316 | Indicative timescale |  | local planning authority | 2014-05-16 | 2014-05-17 | 1
317
318
319
320
321
322
323
324
325
326
327
328
329
330
| Publication of pre-referendum information statement and specified documents |  |  | 2014-05-17 | 2014-05-18 | 1
331 | Indicative timescale |  | electoral services | 2014-05-17 | 2014-05-18 | 1
332
333
334
335
336
337
338
339
340
341
342
343
344
345
| Referendum | 28/56 day minimum |  | 2014-05-19 | 2014-06-16 | 28
346 | Indicative timescale |  | electoral services | 2014-05-19 | 2014-06-16 | 28
347
348
349
350
351
352
353
354
355
356
357
358
359
360
| Publication of referendum decision and making of the Neighbourhood Development Plan |  |  | 2014-06-17 | 2014-06-18 | 1
361 | Indicative timescale |  | local planning authority | 2014-06-17 | 2014-06-18 | 1
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
Test
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
Formulas:
start = IF(MIN([start, row below]:E21)=0,"",MIN([start, row below]:E21))
finish = IF(MAX([finish, row below]:F21)=0,"",MAX([finish, row below]:F21))

## Gantt
Gantt Chart
| START | END | 2013-04-01 | 2013-04-08 | 2013-04-15 | 2013-04-22 | 2013-04-29 | 2013-05-06 | 2013-05-13 | 2013-05-20 | 2013-05-27 | 2013-06-03 | 2013-06-10 | 2013-06-17 | 2013-06-24 | 2013-07-01 | 2013-07-08 | 2013-07-15 | 2013-07-22 | 2013-07-29 | 2013-08-05 | 2013-08-12 | 2013-08-19 | 2013-08-26 | 2013-09-02 | 2013-09-09 | 2013-09-16 | 2013-09-23 | 2013-09-30 | 2013-10-07 | 2013-10-14 | 2013-10-21 | 2013-10-28 | 2013-11-04 | 2013-11-11 | 2013-11-18 | 2013-11-25 | 2013-12-02 | 2013-12-09 | 2013-12-16 | 2013-12-23 | 2013-12-30 | 2014-01-06 | 2014-01-13 | 2014-01-20 | 2014-01-27 | 2014-02-03 | 2014-02-10 | 2014-02-17 | 2014-02-24 | 2014-03-03 | 2014-03-10 | 2014-03-17 | 2014-03-24 | 2014-03-31 | 2014-04-07 | 2014-04-14 | 2014-04-21 | 2014-04-28 | 2014-05-05 | 2014-05-12 | 2014-05-19 | 2014-05-26 | 2014-06-02 | 2014-06-09 | 2014-06-16 | 2014-06-23 | 2014-06-30 | 2014-07-07 | 2014-07-14 | 2014-07-21 | 2014-07-28 | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22
Scoping aims for neighbourhood area/forum application | 2013-04-01 | 2013-05-01 |  | X | X | X | X
Submission of neighbourhood area application | 2013-05-01 | 2013-05-15 | [5 empty] | X | X
Publicity for neighbourhood area application | 2013-05-16 | 2013-06-27 | [7 empty] | X | X | X | X | X | X
Determination of neighbourhood area application | 2013-06-28 | 2013-08-09 | [13 empty] | X | X | X | X | X | X
Publicity for the designation of a neighbourhood area | 2013-08-10 | 2013-08-17 | [19 empty] | X
Submission of a neighbourhood forum application | 2013-05-01 | 2013-05-15 | [5 empty] | X | X
Publicity for the designation of a neighbourhood forum | 2013-05-16 | 2013-06-27 | [7 empty] | X | X | X | X | X | X
Determination of a neighbourhood forum application | 2013-06-28 | 2013-08-09 | [13 empty] | X | X | X | X | X | X
Publicity of the designation of a neighbourhood forum | 2013-08-10 | 2013-08-17 | [19 empty] | X
Preparation of the Neighbourhood Development Plan: community engagement | 2013-04-01 | 2013-10-21 |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Preparation of the Neighbourhood Development Plan: evidence gathering | 2013-04-01 | 2013-10-21 |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Preparation of the Neighbourhood Development Plan: appraisals | 2013-06-28 | 2013-10-21 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Preparation of the Neighbourhood Development Plan: drafting | 2013-06-28 | 2013-10-21 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Pre-submission consultation and publicity of the proposed Neighbourhood Development Plan | 2013-10-22 | 2013-12-03 | [30 empty] | X | X | X | X | X | X
Revisions to draft Neighbourhood Development Plan | 2013-12-04 | 2014-01-03 | [36 empty] | X | X | X | X
Submission of draft Neighbourhood Development Plan to the Local Planning Authority | 2014-01-04 | 2014-01-05
Publication of Neighbourhood Development Plan | 2014-01-06 | 2014-02-17 | [41 empty] | X | X | X | X | X
Appointment of Examiner | 2014-01-06 | 2014-02-10 | [41 empty] | X | X | X | X
Submit plan for examination | 2014-02-18 | 2014-02-19
Examination | 2014-04-03 | 2014-05-15 | [53 empty] | X | X | X | X | X | X
Council consideration of the Examiner's recommendations | 2014-04-03 | 2014-05-15 | [53 empty] | X | X | X | X | X | X
Publication of Examiner's Report and Decision Statement | 2014-05-16 | 2014-05-17
Publication of pre-referendum information statement and specified documents | 2014-05-17 | 2014-05-18
Referendum | 2014-05-19 | 2014-06-16 | [60 empty] | X | X | X
Publication of referendum decision and making of the Neighbourhood Development Plan | 2014-06-17 | 2014-06-18
Test
Key:
Local Authority responsibility